Communication

| Date | 9 july 2026 |
| --- | --- |
| Team ID | XXXXXX |
| Project Name | Strategic product placement analysis |
| Maximum Marks | 1 Mark |

Communication Plan:

Effective communication is essential for a successful project demonstration. This document outlines the communication strategy used within the team and with stakeholders throughout the project lifecycle, including how updates, issues, and feedback were managed.

| S.No | Communication Type | Frequency | Channel / Tool | Participants | Purpose |
| --- | --- | --- | --- | --- | --- |
| 1 | Team Standup | Daily | MS Teams / Slack | All Team Members | Sync daily tasks, track progress, and unblock immediate issues. |
| 2 | Progress Update | Weekly | Email / MS Word Doc | Project Sponsor, Team Members | Share milestone status reports and key analytics insights. |
| 3 | Issue / Bug Discussion | As Needed | Jira / Discord | Relevant Developers & Analysts | Resolve data collection errors or product modeling issues quickly. |
| 4 | Stakeholder Review | Bi-Weekly | Zoom Video Call | Client, Team Lead, Key Stakeholders | Present interim analysis findings and gather strategic feedback. |
| 5 | Final Demo Rehearsal | Once | Meeting Room / Teams | Full Team, Project Manager | Do a dry run of the placement presentation before the client demo. |
| 6 | Final Client Delivery | Once | Presentation / Email | Clients, Executive Stakeholders | Deliver the complete product placement report and core insights. |

Communication Challenges & Resolutions

| S.No | Challenge Faced | Resolution / Action Taken |
| --- | --- | --- |
| 1 | Differing availability and scheduling conflicts for sync meetings among team members. | Established a dedicated weekly slot using shared calendars and recorded all live sessions for offline review. |
| 2 | Misalignment on data terminology and specific definitions for "strategic product placement" metrics. | Documented a unified project glossary in a shared workspace to keep all analytical metrics standardized. |
| 3 | Project updates and file versions getting lost across multiple unorganized communication channels. | Maintained a single, authoritative repository for final documents and streamlined all primary updates via a main thread. |